# Strategic Planning Process: Phase 1

Clarifying who we are, informed by perceptions from our wider community

| ### Process Step | ### Participants | ### Dates/Deadlines |
| --- | --- | --- |
| Survey of all Stakeholders: Staff, Board, Volunteers, Families, Partners – launched at the 2023 Visions of Community Conference | 79 Families, Volunteers, Partners, Staff and Board | DONE Spring 2023 |
| FCSN Staff invited to recommend stakeholders for consultant interviews | Staff | DONE Summer 2023 |
| Interviews with external stakeholders | 24 Partners, Volunteers and Families | DONE Fall 2023 |
| Report and Process Timeline from Consultant shared with Board and 3 board volunteers recruited to participate in Core Values working group: Susan Hutman, Joe Petner, John Reichenbach | Board | DONE Winter 2023-24 |
| Report and Process Timeline shared with Staff and volunteers solicited for Core Values Working Group: Ingrid Arvidson, Meghan Chapman, Ruth Diaz, Rebecca Davis, Sarah Forster, Darla Gundler, Shey Jaboin, Bridget Koetsch, Mary-Beth Landy, Melanie McLaughlin, Mikayla Metcalf, Pam Nourse, Chetna Putta, Rosalie Rippey, Cambria Russell, Monserrate Somers, Ann Teng | Staff | DONE Winter 2023-24 |
| Retreat held for members of Core Values Working Group to create a first draft of Core Values | 17 Staff 3 Board | DONE January 18, 2024 |
| Draft Core Values discussed in a series of small group meetings including 8 for staff and 1 for the full Board. | Staff Board | DONE |
| Revised Core Values shared with all staff, with final opportunity for comment. | Staff | DONE |
| Board Meeting includes proposed core values for consideration, discussion, and vote. | Board | DONE – March 18 refinements recommended |
| In-Person Mission Statement generation meeting with Federation Staff and Board. Vision Statement will also be discussed and potentially revised. | All Staff Full Board | DONE March 21 |
| Subcommittee is appointed by the Executive Director to wordsmith final draft of changes agreed upon in the Mission Statement meeting. | Staff Volunteers | DONE |
| Pam, Amanda Rosalie meet to review and finalize a draft | PN, AG, RR | DONE |
| Survey on Mission Statement shared with staff and Board via survey to solicit final comments. | Board and Staff | DONE |
| Mission, Vision/Aspiration Statement, and refined Core Values approved by Board | Board | May 20 |
| Survey requesting proposals for a new name for the Federation | Board and Staff | Late May |
| A task force convened by the Executive Director proposes 3 – 5 options for a New Name for the Federation. | Staff and Board | Completed by June 15 |
| Staff surveyed on proposed options for a New Name. | Staff | End of June |
| Board votes on a New Name for the Federation. | Board | Board meeting to vote – TBD |

# Phase 2: Development of Strategic Priorities & Plan

Partnering with Families, Partners, Volunteers and Stakeholders 
to Develop Our Vision and Chart Our Course

Detailed timeline to come!